## CDI2 Setup
No. | Task | info
1 | ETL Data Understanding Call (EH Hrs: 1)
2 | Align AWS and Snowflake Access (EH Hrs: X) | depending in task before
3 | Plan Onboarding tasks (EH Hrs: 2) | depending in task before
4 | Setup CDI2 Infra on AWS (EH Hrs: 5) | depending in task before
5 | Setup Tracking Infra on AWS (EH Hrs: 3) | depending in task before
6 | Setup GTM Tracking (EH Hrs : 2) | depending in task before
7 | Setup snowpipe (EH Hrs: 3) | depending in task before
8 | Configure CircleCI to access Github and AWS (EH Hrs: 1) | depending in task before
9 | Create Snowflake Schemas (EH Hrs: 4) | depending in task before
10 | Configure Airflow to access Snowflake (EH Hrs: 1) | depending in task before
11 | Setup Channel Definition Parsing Submodule and Deploy for Client (EH Hrs: 4) | in parallel possible
12 | Setup Web Session Module (EH Hrs: 8)
13 | Setup User Matching (EH Hrs: 6)
14 | Backend CRM connection and data import (EH Hrs: X)
15 | Create Custom Conversion Import Module (EH Hrs: 8)
16 | Set-Up Session Costs Submodule and Deploy for Client (EH Hrs: 8)
17 | Verification with client: Channel Traffic stats and platform costs (EH Hrs: 4) | depending in task before
18 | Setup Attribution Submodule (EH Hrs: 8) | depending in task before
19 | Share first Attribution Reports & CJ Stats with client (EH Hrs: 6) | depending in task before
20 | implement snowflake cost monitoring with dbt (EH Hrs: X) | in parallel possible
21 | Setup Google Upload Submodule (EH Hrs: 6)
22 | setup Facebook Upload Submodule (EH Hrs: 6)
23 | Intense Data Checks & Verification with the client (EH Hrs: 8) | depending in task before
24 | Technical System Documentieon & Data-Usage Documentation in Google Docs (EH Hrs: 5) | depending in task before